## Sheet1
SHRFV Project Implementation Plan 2018 / 19
Key tasks | Lead | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June
Element 1 Engage leadership & build momentum
Senior management engagement & briefings | Lead: Project Mngr (PM)
Determine Executive sponsor | Lead: CEO
Determine project objectives | Lead: Project Sponsor (PS)
Establish terms of reference | bar: Lead; Aug
Establish reference group | bar: Lead; Aug
Communication planning | Lead: PM /Comms
Release FV position statement | Lead: CEO
Project launch | bar: Lead; Sept
Other tasks | bar: Oct
Element 2 Lay a foundation for success
Develop policy & procedure for staff | bar: Aug to Sept
Workplace support training for managers | bar: Oct to Nov
Workplace support intranet page
Service mapping
Develop policy and procedure for patients
Other tasks
Element 3 Build capacity and capability
Module I Shared understanding training | bar: Oct to Nov
Module 2 Clinical practice training
Supplementary training elder abuse
Supplementary training sexual assault
etc
Element 4 Build partnerships
Meet with referral partners | bar: Aug
Host / participate in community event
Involve patients
etc
Element 5 Create the evidence base
Collate data | bar: July
Evaluate using the evaluation framework | bar: June